## Sheet1
TASKS | Day | Priority | Status | Est MD | Actual MD | Category | Dev | Notes
Discussion of the new requirements | Thursday | 1 | Done | .2MD | .2MD | PLAN | GROUP1
Create a plan | Thursday | 1 | Done | .3 MD | .3 MD | PLAN | BARREPE
Usecase Diagram | Thursday | 2 | Done | .1 MD | .1 MD | UML | ANDESMA
Sequence Diagram | Thursday | 2 | Done | .1 MD | .1 MD | UML | ANDESMA
ERD Design | Thursday | 1 | Done | .2MD | .1MD | SQL | DEQUIAL
Normalization | Thursday | 1 | Done | .2MD | .1MD | SQL | DEQUIAL
Database Creation and Scripts | Thursday | 1 | Done | .2MD | .1MD | SQL | DEQUIAL
Create system body in STS (Packages, Folder Structure) | Thursday | 1 | Done | .3MD | .3MD | PROJECT | RACELPA
Create Entity of tables based on ERD | Thursday | 1 | Done | .2 MD | .2 MD | PROJECT | RACELPA
Create the DAO and Impl (initial for testing) | Thursday | 1 | Done | .3MD | .3MD | PROJECT | RACELPA
Autowired DAO in Controllers | Thursday | 1 | Done | .1 MD | .1 MD | PROJECT | LIMOSJO
Create a simple transaction through DB using the created DAO | Thursday | 1 | Done | .3MD | .3MD | PROJECT | DELEOAN
Homepage Design | Thursday | 2 | Done | .2 MD | .2MD | UI | ANDESMA
Image logo | Thursday | 2 | Done | .1MD | .1MD | UI | BARREPE
Popup windows clean | Thursday | 2 | Done | .2 MD | .2MD | UI | DEQUIAL
Finish the new DAO and Impl of the last project | Friday | 1 | Done | .5MD | .5 MD | PROJECT | RACELPA LIMOSJO DELOAN
JMS structure body and working initial project | Friday | 1 | Done | .2 MD | .5MD | PROJECT | DEQUIAL
Explore and Test Generic DAO implementation | Friday | 2 | Done | .2 MD | .2 MD | PROJECT | BARREPE
JMS service with controller service | Friday | 2 | Done | .3 MD | .3 MD | PROJECT | DEQUIAL
Edit profile functions and UI | Friday | 1 | Done | .5 MD | .5 MD | PROJECT | ANDESMA
UI design for my profile, register login menu | Friday | 2 | Done | .3 MD | .3 MD | PROJECT | ANDESMA
Alerts design | Friday | 2 | Done | .2 MD | .2 MD | PROJECT | ANDESMA
Application of Generic DAO and changing code in implementation | Saturday | 1 |  | .4 MD |  | PROJECT | GROUP1
Logger Implementation | Saturday | 1 | Done | .1 MD | .1 MD | PROJECT | RACELPA
Listener Implementation | Saturday | 1 | Done | .1 MD | .1MD | PROJECT | DELOAN
Filters Implementation | Saturday | 1 | Done | .1 MD | .1MD | PROJECT | LIMOSJO
Session Application | Saturday | 1 | Done | .3 MD | .3 MD | PROJECT | DELOAN
Integrate JMS to WebProject | Saturday | 1 | Done | .3MD | .3MD | PROJECT | GROUP1
Creating a junit testing | Saturday | 2 | Done | .3MD | .3MD | TESTING | DEQUIAL
Admin View | Saturday | 2 | Done | .3 MD | .3MD | UI | ANDESMA
Class diagram | Sunday | 1 | Done | .2MD | .2MD | UML | BARREPE RACELPA
Powerpoint | Sunday | 2 | Done | .1 MD | .1 MD | PPT | BARREPE
contact us | Sunday | 2 | Done | .5 MD | .5MD | UI | ANDESMA
Application of Generic DAO and changing code in implementation | Sunday | 1 | Not implemented | .2 MD |  | PROJECT | DEQUIAL BARREPE
JAVA DOC | Sunday | 1 | Done | .2MD | .2MD | JAVA DOC | GROUP1
Functional Testing | Sunday | 2 | Partial | .2MD |  | TESTING | BARREPE
User testing | Sunday | 2 | Partial | .1MD |  | TESTING | BARREPE