## Sheet1
TASKS | Day | Priority | Status | Est MD | Actual MD | Category | Dev | Notes
Brainstorm | Tuesday | 1 | Done | .3MD |  | PROJECT | GROUP 1
Revamp Project Structure | Tuesday | 1 | Done | .1MD |  | PROJECT | BARREPE
Application of GenericDAO | Tuesday | 1 | Done | .1MD |  | PROJECT | BARREPE
Clear numeric fields | Tuesday | 2 |  | .2 MD |  | UI | ANDESMA
Database Script and ERD | Tuesday | 1 |  | .2 MD |  | ERD | DEQUIAL
Explore JMS (Project behavior) | Tuesday | 1 |  | .2MD |  | PROJECT | DEQUIAL
Integrate Initial UI panels | Tuesday | 1 |  | .2 MD |  | UI | LIMOSJO
Initialize UI panels for Admin | Tuesday | 1 |  | .2 MD |  | UI | RACELPA DELOAN LIMOSJO
Integrate Initial UI panels and DOM | Wednesday | 1 |  | .2 MD |  | PROJECT | GROUP1
Integrate JMS and Web Project | Wednesday | 1 |  | .3 MD |  | PROJECT | GROUP 1
Finish DOM Services plus the ADMIN | Wednesday | 1 |  | .5MD |  | PROJECT | BARREPE
Finish JMS in Web Project | Wednesday | 1 |  | .5MD |  | PROJECT | DEQUIAL
Finish panels for admin page | Wednesday | 1 |  | .5 MD |  | UI | ANDESMA DELOAN LIMOSJO RACELPA
Finish Integration UI and DOM | Thursday | 1 |  | .5 MD |  | PROJECT | GROUP 1
Functional Testing | Thursday | 1 |  | .1 MD |  | TESTING | BARREPE
User Testing | Thursday | 1 |  | .1 MD |  | TESTING | BARREPE
UML | Thursday | 2 |  | .3 MD |  | UML | ANDESMA
ERD | Thursday | 2 |  | .2 MD |  | ERD | DEQUIAL
JAVADOC | Thursday | 1 |  | .1 MD |  | DOC | LIMOSJO
PPT | Thursday | 2 |  | .3 MD |  | DOC | GROUP1
MOCK Presentation | Thursday | 1 |  | .1MD |  | PRESENTATION | GROUP1
Code Review | Thursday | 1 |  | .2MD |  | REVIEW | BARREPE